## HD Status
Fleet Department Status Report For The Fire Department Heavy Duty Shop
|  |  | Today's Date: | [7 empty] | 2018-01-16 | [5 empty] | 43173.5041 |  |  |  | Edited By: |  |  |  |  | Lloyd Spevack
Category | [7 empty] | Total Inventory |  | A |  |  | B |  | C |  |  | D | E | F |  |  | G | H |  |  | Total Down |  | Total Ready |  | Vehicle Availability
[10 empty] | Waiting For Assignment |  |  | Waiting On Shop Space |  | Waiting On Parts |  |  | Work In Progress | At Vendor Or Other Shop Location | Bay Space Unavailable |  |  | Pending Outside Services | Awaiting Department Authorization
HFD Units In Body Shop For Repairs -----> | [7 empty] | 9
HFD - First Line Engines | [7 empty] | 88 |  | 0 |  |  | 0 |  | 3 |  |  | 8 | 2 | 0 |  |  | 0 | 0 |  |  | 13 |  | 75 |  | 85.23%
HFD - Reserve Engines |  |  |  | Issued: |  | 14 |  | 24 |  | 0 |  |  | 0 |  | 0 |  |  | 2 | 1 | 0 |  |  | 0 | 0 |  |  | 3 |  | 8 |  | 33.33%
HFD - First Line Ladders | [7 empty] | 38 |  | 0 |  |  | 0 |  | 2 |  |  | 1 | 3 | 0 |  |  | 0 | 0 |  |  | 6 |  | 32 |  | 84.21%
HFD - Reserve Ladders |  |  |  | Issued: |  | 12 |  | 16 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 |  | 4 |  | 25%
HFD - Breathing Air Units | [7 empty] | 4 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 1 | 0 |  |  | 0 | 0 |  |  | 1 |  | 3 |  | 75%
HFD - Reserve Cascade |  |  |  | Issued: |  | 1 |  | 2 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 |  | 0 |  | 0%
HFD - Haz-Mat Units | [7 empty] | 6 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 |  | 6 |  | 100%
HFD - Reserve Haz-Mat Units |  |  |  | Issued: |  | 0 |  | 2 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 |  | 1 |  | 50%
HFD - Rescue Units | [7 empty] | 6 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 |  | 6 |  | 100%
HFD - Reserve Rescue Units |  |  |  | Issued: |  | 1 |  | 1 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 |  | 1 |  | 100%
HFD - Special Equipment | [7 empty] | 5 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 1 | 0 |  |  | 0 | 0 |  |  | 1 |  | 4 |  | 80%
Totals -----> | [7 empty] | 192 |  | 0 |  |  | 0 |  | 5 |  |  | 11 | 8 | 0 |  |  | 0 | 0 |  |  | 24 |  | 168 |  | 87.5%
Unit Number | Status | Alternate Unit Number |  |  | Year |  | Make |  | Reserve Number |  |  | WO Number |  | Date | Days Down | Diagnosis - Comment | [5 empty] | Notes |  |  | Vendor Or Technician |  |  | Date To Outside Shop-Vendor |  | Original Estimated Completion Date |  | Revised Estimated Completion Date
Units At Vendor For Repair
34892 | E | L-045 |  |  | 2004 |  | E-One |  | RL-011 |  |  | 2960563 |  | 2017-05-08 | 310 | LADDER PAD MOUNT BROKEN. | [5 empty] | Diagnosing In Progress |  |  | HALLMARK |  |  |  |  | 2017-06-30 |  | 2017-01-19
34837 | E | E-065 |  |  | 2004 |  | E-One |  | RE-019 |  |  | 2958314 |  | 2017-05-23 | 295 | Accident Repairs / Electrical Repairs | [5 empty] | Work In Progress |  |  | HALLMARK |  |  | 2017-11-13 |  | 2017-06-30 |  | 2017-01-19
41334 | E | MC-008 |  |  | 2009 |  | Spartan |  |  |  |  | MWO |  | 2017-12-08 | 96 | OUT RIGGERS | [5 empty] | Work In Progress |  |  | METRO-FIRE |  |  | 2017-12-08 |  | 2017-12-28 |  | 2017-01-30
35559 | E | L-019 |  |  | 2005 |  | Ferrara |  | RL-010 |  |  | 3010581 |  | 2017-12-17 | 87 | RUNNING ROUGH | [5 empty] | Work In Progress |  |  | RUSH RUCK |  |  | 2017-11-25 |  | 2017-12-15 |  | 2017-01-30
43199 | E | L-068 |  |  | 2013 |  | Spartan |  | RL-003 |  |  | 3028400 |  | 2017-12-19 | 85 | BROKEN WATERWAY | [5 empty] | Diagnosing In Progress |  |  | METRO FIRE |  |  | 2017-12-19 |  | 2017-12-29 |  | 2017-01-30
34198 | E | E-027 |  |  | 2003 |  | E-One |  | RE-004 |  |  | 3031789 |  | 2018-01-03 | 70 | HEAD GASKET | [5 empty] | Waiting on Estimates |  |  | RUSH TRUCK |  |  | 2018-01-09 |  | 2017-01-19
37693 | E | E-044 |  |  | 2007 |  | Ferrara |  | RE-014 |  |  | 3032845 |  | 2018-01-05 | 68 | TRANS MALFUNCTION | [5 empty] | Diagnosing In Progress |  |  | RELIABLE |  |  | 2018-01-05 |  | 2017-01-19
41845 | E | AIR-023 |  |  | 2011 |  | Ford |  | RCAS-002 |  |  | 3033237 |  | 2018-01-09 | 64 | TURBO | [5 empty] | Diagnosing In Progress |  |  | TOMMIE VAUGHN |  |  | 2018-01-09 |  | 2017-01-30
Units In Shop For Repair
39093 | D | E-067 |  |  | 2009 |  | Ferrara |  | RE-006 |  |  | 2948896 |  | 2017-03-29 | 350 | Burnt Wiring Harness | [5 empty] | Work In Progress |  |  | Nino |  |  |  |  | 2017-06-30 |  | 2017-01-30
34753 | D | L-101 |  |  | 2004 |  | E-One |  | RE-013 |  |  | 2968560 |  | 2017-06-05 | 282 | Air Brakes Sys. Leaks / Aerial Ladder Adjustment | [5 empty] | Work In Progress |  |  | David |  |  |  |  | 2017-06-30 |  | 2017-01-30
35698 | D | E-002 |  |  | 2005 |  | Ferrara |  | RE-012 |  |  | 2962660 |  | 2017-06-27 | 260 | Pump Sys. Malfunctioned | [5 empty] | WAITING ON PARTS |  |  | STEVE |  |  |  |  | 2017-08-24 |  | 2017-01-30
29935 | D | RE-023 |  |  | 1999 |  | E-One |  |  |  |  | 2983606 |  | 2017-07-05 | 252 | Water Tank Leaking | [5 empty] | Work In Progress |  |  | Marcelo |  |  |  |  | 2017-08-31 |  | 2017-01-30
29997 | D | E-071 |  |  | 1999 |  | E-One |  | RE-005 |  |  | 2993577 |  | 2017-08-26 | 200 | MOTOR FLOOD DAMAGE | [5 empty] | Diagnosing In Progress |  |  | Steve |  |  |  |  | 2017-10-15 |  | 2017-01-30
31576 | D | E-072 |  |  | 2000 |  | E-One |  | RE-018 |  |  | 2993539 |  | 2017-08-26 | 200 | MOTOR FLOOD DAMAGE | [5 empty] | Diagnosing In Progress |  |  | Jesse |  |  |  |  | 2017-10-15 |  | 2017-01-30
34836 | D | E-093 |  |  | 2004 |  | E-One |  | RE-001 |  |  | 2993578 |  | 2017-08-26 | 200 | FLOOD DAMAGE, MOTOR | [5 empty] | Diagnosing In Progress |  |  | JESSE |  |  |  |  | 2017-10-15 |  | 2017-01-30
30566 | D | RE-041 |  |  | 1999 |  | E-One |  |  |  |  | 2993633 |  | 2017-08-27 | 199 | FLOOD DAMAGE, NEEDS ENGINE | [5 empty] | Diagnosing In Progress |  |  | Louis |  |  |  |  | 2017-10-15 |  | 2017-01-30
35697 | C | E-008 |  |  | 2005 |  | Ferrara |  | OLD E-508 |  |  | 2995132 |  | 2017-09-02 | 193 | PUMP SYSTEM, MECHANICAL SEAL, IMPELLER | [5 empty] | WAITING ON PARTS |  |  | Steve |  |  |  |  | 2017-10-15 |  | 2017-01-30
34764 | C | E-077 |  |  | 2005 |  | Ferrara |  | RE-069 |  |  | 3002829 |  | 2017-09-20 | 175 | CAUGHT ON FIRE ON FIRE SCENE | [5 empty] | WAITING ON PARTS |  |  | Nino |  |  |  |  | 2017-12-15 |  | 2017-01-30
34762 | C | E-036 |  |  | 2005 |  | Ferrara |  | RE-037 |  |  | 3002627 |  | 2017-09-28 | 167 | DRIVE-SHAFT MALFUNCTIONED | [5 empty] | WAITING ON PARTS |  |  | STEVE |  |  |  |  | 2017-12-15 |  | 2017-01-30
31574 | D | RE-002 |  |  | 2000 |  | E-One |  |  |  |  | 3002997 |  | 2017-09-28 | 167 | MOTOR FRONT COVER CRACKED | [5 empty] | Work In Progress |  |  | NINO |  |  |  |  | 2017-12-15 |  | 2017-01-30
34815 | C | L-071 |  |  | 2004 |  | E-One |  | RL-012 |  |  | 3011546 |  | 2017-10-25 | 140 | GENERATOR MALFUNCTION | [5 empty] | Work In Progress |  |  | HARRISON |  |  | 2017-10-25 |  | 2017-12-15 |  | 2017-01-30
31132 | C | L-044 |  |  | 2000 |  | E-One |  | RL-007 |  |  | 3020456 |  | 2017-11-27 | 107 | OUTRIGGER LEAK | [5 empty] | WAITING ON PARTS |  |  | DAVID |  |  |  |  | 2017-12-15 |  | 2017-01-30
34760 | D | E-064 |  |  | 2005 |  | Ferrara |  | RE-015 |  |  | 3022818 |  | 2017-12-04 | 100 | BROKEN T-CASE MOUNTS | [5 empty] | Work In Progress |  |  | JESSE |  |  |  |  | 2017-12-28 |  | 2017-01-30
39096 | D | E-035 |  |  | 2009 |  | Ferrara |  | RE-016 |  |  | 3021365 |  | 2017-12-31 | 73 | BODYSHOP | [13 empty] | 2017-01-19
39482 | D | L-051 |  |  | 2009 |  | Ferrara |  | RL-029 |  |  | 3035059 |  | 2018-01-13 | 60 | BROKEN LADDER | [5 empty] | Diagnosing In Progress |  |  | NINO |  |  |  |  | 2017-03-30