## HD Status
Fleet Department Status Report For The Fire Department Heavy Duty Shop
|  |  | Today's Date: | [7 empty] | 2018-02-08 | [5 empty] | 43174.5001 |  |  |  | Edited By: |  |  |  |  | Lloyd Spevack
Category | [7 empty] | Total Inventory |  | A |  |  | B |  | C |  |  | D | E | F |  |  | G | H |  |  | Total Down |  | Total Ready |  | Vehicle Availability
[10 empty] | Waiting For Assignment |  |  | Waiting On Shop Space |  | Waiting On Parts |  |  | Work In Progress | At Vendor Or Other Shop Location | Bay Space Unavailable |  |  | Pending Outside Services | Awaiting Department Authorization
HFD Units In Body Shop For Repairs -----> | [7 empty] | 6
HFD - First Line Engines | [7 empty] | 88 |  | 0 |  |  | 0 |  | 3 |  |  | 4 | 5 | 0 |  |  | 0 | 0 |  |  | 12 |  | 76 |  | 86.36%
HFD - Reserve Engines |  |  |  | Issued: |  | 14 |  | 24 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 1 | 0 |  |  | 0 | 0 |  |  | 1 |  | 7 |  | 29.17%
HFD - First Line Ladders | [7 empty] | 38 |  | 0 |  |  | 0 |  | 2 |  |  | 3 | 3 | 0 |  |  | 0 | 0 |  |  | 8 |  | 30 |  | 78.95%
HFD - Reserve Ladders |  |  |  | Issued: |  | 11 |  | 16 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 |  | 5 |  | 31.25%
HFD - Breathing Air Units | [7 empty] | 4 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 |  | 4 |  | 100%
HFD - Reserve Cascade |  |  |  | Issued: |  | 1 |  | 2 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 |  | 0 |  | 0%
HFD - Haz-Mat Units | [7 empty] | 6 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 |  | 6 |  | 100%
HFD - Reserve Haz-Mat Units |  |  |  | Issued: |  | 0 |  | 2 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 |  | 1 |  | 50%
HFD - Rescue Units | [7 empty] | 6 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 |  | 6 |  | 100%
HFD - Reserve Rescue Units |  |  |  | Issued: |  | 1 |  | 1 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 |  | 1 |  | 100%
HFD - Special Equipment | [7 empty] | 5 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 |  | 5 |  | 100%
Totals -----> | [7 empty] | 192 |  | 0 |  |  | 0 |  | 5 |  |  | 7 | 9 | 0 |  |  | 0 | 0 |  |  | 21 |  | 168 |  | 87.5%
Unit Number | Status | Alternate Unit Number |  |  | Year |  | Make |  | Reserve Number |  |  | WO Number |  | Date | Days Down | Diagnosis - Comment | [5 empty] | Notes |  |  | Vendor Or Technician |  |  | Date To Outside Shop-Vendor |  | Original Estimated Completion Date |  | Revised Estimated Completion Date
Units At Vendor For Repair
34892 | E | L-045 |  |  | 2004 |  | E-One |  | RL-011 |  |  | 2960563 |  | 2017-05-08 | 311 | LADDER PAD MOUNT BROKEN. | [5 empty] | Diagnosing In Progress |  |  | HALLMARK |  |  |  |  | 2017-06-30 |  | 2018-02-22
34837 | E | E-065 |  |  | 2004 |  | E-One |  | RE-019 |  |  | 2958314 |  | 2017-05-23 | 296 | Accident Repairs / Electrical Repairs | [5 empty] | Work In Progress |  |  | HALLMARK |  |  | 2017-11-13 |  | 2017-06-30 |  | 2018-02-22
31574 | E | RE-002 |  |  | 2000 |  | E-One |  |  |  |  | 3002997 |  | 2017-09-28 | 168 | MOTOR FRONT COVER CRACKED | [5 empty] | Work In Progress |  |  | S & S |  |  | 2018-01-25 |  | 2017-12-15 |  | 2018-02-22
35559 | E | L-019 |  |  | 2005 |  | Ferrara |  | RL-010 |  |  | 3010581 |  | 2017-12-17 | 88 | RUNNING ROUGH | [5 empty] | Work In Progress |  |  | RUSH RUCK |  |  | 2017-11-25 |  | 2017-12-15 |  | 2018-02-22
43199 | E | L-068 |  |  | 2013 |  | Spartan |  | RL-003 |  |  | 3028400 |  | 2017-12-19 | 86 | BROKEN WATERWAY | [5 empty] | Diagnosing In Progress |  |  | METRO FIRE |  |  | 2017-12-19 |  | 2017-12-29 |  | 2018-02-22
34198 | E | E-027 |  |  | 2003 |  | E-One |  | RE-004 |  |  | 3031789 |  | 2018-01-03 | 71 | HEAD GASKET | [5 empty] | Waiting on Estimates |  |  | RUSH TRUCK |  |  | 2018-01-09 |  | 2017-01-19 |  | 2018-02-22
37693 | E | E-044 |  |  | 2007 |  | Ferrara |  | RE-007 |  |  | 3032845 |  | 2018-01-05 | 69 | TRANS MALFUNCTION | [5 empty] | Diagnosing In Progress |  |  | RELIABLE |  |  | 2018-01-05 |  | 2017-01-19 |  | 2018-02-22
39482 | E | L-051 |  |  | 2009 |  | Ferrara |  | RL-029 |  |  | 3035059 |  | 2018-01-13 | 61 | BROKEN / DAMAGED AERIAL LADDER | [5 empty] | Work In Progress |  |  | METRO FIRE |  |  | 2018-01-22 |  | 2017-03-30
35556 | E | L-038 |  |  | 2005 |  | Ferrara |  | RL-011 |  |  | 2995857 |  | 2018-01-18 | 56 | INJECTORS | [5 empty] | Diagnosing In Progress |  |  | RUSH TRUCK |  |  | 2018-01-18 |  | 2018-02-22
42046 | E | E-058 |  |  | 2012 |  | Ferrara |  | R-17 |  |  | 3039523 |  | 2018-01-31 | 43 | CRACKED FLYWHEEL | [5 empty] | Diagnosing In Progress |  |  | RUSH TRUCK |  |  | 2018-02-01 |  | 2018-02-22
41858 | E | E-025 |  |  | 2011 |  | Spartan |  | RE-076 |  |  | 3041054 |  | 2018-02-06 | 37 | PINION BEARING | [5 empty] | Diagnosing In Progress |  |  | METRO FIRE |  |  | 2018-02-07 |  | 2018-02-22
Units In Shop For Repair
39093 | D | E-067 |  |  | 2009 |  | Ferrara |  | RE-006 |  |  | 2948896 |  | 2017-03-29 | 351 | Burnt Wiring Harness | [5 empty] | Work In Progress |  |  | Nino |  |  |  |  | 2017-06-30 |  | 2018-02-22
34753 | D | L-101 |  |  | 2004 |  | E-One |  | RE-013 |  |  | 2968560 |  | 2017-06-05 | 283 | Air Brakes Sys. Leaks / Aerial Ladder Adjustment | [5 empty] | Work In Progress |  |  | David |  |  |  |  | 2017-06-30 |  | 2018-02-22
35698 | D | E-002 |  |  | 2005 |  | Ferrara |  | RE-012 |  |  | 2962660 |  | 2017-06-27 | 261 | Pump Sys. Malfunctioned | [5 empty] | WAITING ON PARTS |  |  | STEVE |  |  |  |  | 2017-08-24 |  | 2018-02-22
29935 | D | RE-023 |  |  | 1999 |  | E-One |  |  |  |  | 2983606 |  | 2017-07-05 | 253 | Water Tank Leaking | [5 empty] | Work In Progress |  |  | Marcelo |  |  |  |  | 2017-08-31 |  | 2018-02-22
35697 | C | E-008 |  |  | 2005 |  | Ferrara |  | OLD E-508 |  |  | 2995132 |  | 2017-09-02 | 194 | PUMP SYSTEM, MECHANICAL SEAL, IMPELLER | [5 empty] | WAITING ON PARTS |  |  | Steve |  |  |  |  | 2017-10-15 |  | 2018-02-22
34764 | C | E-077 |  |  | 2005 |  | Ferrara |  | RE-069 |  |  | 3002829 |  | 2017-09-20 | 176 | CAUGHT ON FIRE ON FIRE SCENE | [5 empty] | WAITING ON PARTS |  |  | Nino |  |  |  |  | 2017-12-15 |  | 2018-02-22
34762 | C | E-036 |  |  | 2005 |  | Ferrara |  | RE-037 |  |  | 3002627 |  | 2017-09-28 | 168 | DRIVE-SHAFT MALFUNCTIONED | [5 empty] | WAITING ON PARTS |  |  | STEVE |  |  |  |  | 2017-12-15 |  | 2018-02-22
34815 | C | L-071 |  |  | 2004 |  | E-One |  | RL-012 |  |  | 3011546 |  | 2017-10-25 | 141 | SWIVEL LEAKING | [5 empty] | WAITING ON PARTS |  |  | MARCELO |  |  | 2017-10-25 |  | 2017-12-15 |  | 2018-02-22
31132 | C | L-044 |  |  | 2000 |  | E-One |  | RL-007 |  |  | 3020456 |  | 2017-11-27 | 108 | OUTRIGGER LEAK | [5 empty] | Work In Progress |  |  | DAVID |  |  |  |  | 2017-12-15 |  | 2018-02-22
38405 | D | E-010 |  |  | 2008 |  | Ferrara |  | RE-000 |  |  | MWO |  | 2018-01-20 | 54 | DPF, EGR COOLER | [5 empty] | Diagnosing In Progress |  |  | KERRY |  |  |  |  | 2017-01-30 |  | 2018-02-22
39481 | D | L-033 |  |  | 2009 |  | Ferrara |  | RL-004 |  |  | 3036389 |  | 2018-01-21 | 53 | OIL LEAK | [5 empty] | Work In Progress |  |  | RUSSELL |  |  |  |  | 2017-01-30 |  | 2018-02-22
45401 | D | L-076 |  |  | 2016 |  | Ferrara |  | RL-093 |  |  | 3038470 |  | 2018-01-26 | 48 | HYDRAULIC MALFUNCTION | [5 empty] | WAITING ON PARTS |  |  | STEVE |  |  |  |  | 2018-02-22