## HD Status
Fleet Department Status Report For The Fire Department Heavy Duty Shop
|  |  | Today's Date: | [7 empty] | 2018-03-13 | [5 empty] | 43174.4946 |  |  |  | Edited By: |  |  |  |  | Lloyd Spevack
Category | [7 empty] | Total Inventory |  | A |  |  | B |  | C |  |  | D | E | F |  |  | G | H |  |  | Total Down |  | Total Ready |  | Vehicle Availability
[10 empty] | Waiting For Assignment |  |  | Waiting On Shop Space |  | Waiting On Parts |  |  | Work In Progress | At Vendor Or Other Shop Location | Bay Space Unavailable |  |  | Pending Outside Services | Awaiting Department Authorization
HFD Units In Body Shop For Repairs -----> | [7 empty] | 7
HFD - First Line Engines | [7 empty] | 88 |  | 0 |  |  | 0 |  | 2 |  |  | 4 | 4 | 0 |  |  | 0 | 0 |  |  | 10 |  | 78 |  | 88.64%
HFD - Reserve Engines |  |  |  | Issued: |  | 14 |  | 24 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 |  | 8 |  | 33.33%
HFD - First Line Ladders | [7 empty] | 38 |  | 0 |  |  | 0 |  | 1 |  |  | 5 | 4 | 0 |  |  | 0 | 0 |  |  | 10 |  | 28 |  | 73.68%
HFD - Reserve Ladders |  |  |  | Issued: |  | 10 |  | 16 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 |  | 6 |  | 37.5%
HFD - Breathing Air Units | [7 empty] | 4 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 1 | 0 |  |  | 0 | 0 |  |  | 1 |  | 3 |  | 75%
HFD - Reserve Cascade |  |  |  | Issued: |  | 1 |  | 2 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 |  | 0 |  | 0%
HFD - Haz-Mat Units | [7 empty] | 6 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 1 | 0 |  |  | 0 | 0 |  |  | 1 |  | 5 |  | 83.33%
HFD - Reserve Haz-Mat Units |  |  |  | Issued: |  | 1 |  | 2 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 |  | 0 |  | 0%
HFD - Rescue Units | [7 empty] | 6 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 |  | 6 |  | 100%
HFD - Reserve Rescue Units |  |  |  | Issued: |  | 1 |  | 1 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 |  | 1 |  | 100%
HFD - Special Equipment | [7 empty] | 5 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 |  | 5 |  | 100%
Totals -----> | [7 empty] | 192 |  | 0 |  |  | 0 |  | 3 |  |  | 9 | 10 | 0 |  |  | 0 | 0 |  |  | 22 |  | 167 |  | 86.98%
Unit Number | Status | Alternate Unit Number |  |  | Year |  | Make |  | Reserve Number |  |  | WO Number |  | Date | Days Down | Diagnosis - Comment | [5 empty] | Notes |  |  | Vendor Or Technician |  |  | Date To Outside Shop-Vendor |  | Original Estimated Completion Date |  | Revised Estimated Completion Date
Units At Vendor For Repair
34892 | E | L-045 |  |  | 2004 |  | E-One |  | RL-011 |  |  | 2960563 |  | 2017-05-08 | 311 | LADDER PAD MOUNT BROKEN. | [5 empty] | Diagnosing In Progress |  |  | HALLMARK |  |  |  |  | 2017-06-30 |  | 2018-04-01
34837 | E | E-065 |  |  | 2004 |  | E-One |  | RE-019 |  |  | 2958314 |  | 2017-05-23 | 296 | Accident Repairs / Electrical Repairs | [5 empty] | Work In Progress |  |  | HALLMARK |  |  | 2017-11-13 |  | 2017-06-30 |  | 2018-04-01
38686 | E | HM-022-#2 |  |  | 2008 |  | Ferrara |  |  |  |  | 3011745 |  | 2017-10-25 | 141 | Engine Rebuild | [5 empty] | Work In Progress |  |  | RUSH RUCK |  |  | 2017-10-30 |  | 2018-02-22 |  | 2018-04-01
43199 | E | L-068 |  |  | 2013 |  | Spartan |  | RL-003 |  |  | 3028400 |  | 2017-12-19 | 86 | BROKEN WATERWAY | [5 empty] | Diagnosing In Progress |  |  | METRO FIRE |  |  | 2017-12-19 |  | 2017-12-29 |  | 2018-04-01
34198 | E | E-027 |  |  | 2003 |  | E-One |  | RE-004 |  |  | 3031789 |  | 2018-01-03 | 71 | HEAD GASKET | [5 empty] | Waiting on Estimates |  |  | RUSH TRUCK |  |  | 2018-01-09 |  | 2017-01-19 |  | 2018-04-01
39482 | E | L-051 |  |  | 2009 |  | Ferrara |  | RL-029 |  |  | 3035059 |  | 2018-01-13 | 61 | BROKEN / DAMAGED AERIAL LADDER | [5 empty] | Work In Progress |  |  | METRO FIRE |  |  | 2018-01-22 |  | 2017-03-30 |  | 2018-04-01
35556 | E | L-038 |  |  | 2005 |  | Ferrara |  | RL-011 |  |  | 2995857 |  | 2018-01-18 | 56 | INJECTORS | [5 empty] | Diagnosing In Progress |  |  | RUSH TRUCK |  |  | 2018-01-18 |  | 2018-02-22 |  | 2018-04-01
42046 | E | E-058 |  |  | 2012 |  | Ferrara |  | R-17 |  |  | 3039523 |  | 2018-01-31 | 43 | CRACKED FLYWHEEL | [5 empty] | Diagnosing In Progress |  |  | RUSH TRUCK |  |  | 2018-02-01 |  | 2018-02-22 |  | 2018-04-01
41845 | E | AIR-023 |  |  | 2011 |  | Ferrara |  | RC-002 |  |  | 3045264 |  | 2018-02-20 | 23 | Generator Repairs | [5 empty] | Diagnosing In Progress |  |  | METRO FIRE |  |  | 2018-02-21 |  | 2018-04-01
38742 | E | E-052 |  |  | 2008 |  | Ferrara |  | RE-002 |  |  | 3046313 |  | 2018-03-04 | 11 | Engine Running Rough | [5 empty] | Work In Progress |  |  | RUSH TRUCK |  |  | 2018-03-06 |  | 2018-03-30
Units In Shop For Repair
39093 | D | E-067 |  |  | 2009 |  | Ferrara |  | RE-006 |  |  | 2948896 |  | 2017-03-29 | 351 | Burnt Wiring Harness | [5 empty] | Work In Progress |  |  | STEVE |  |  |  |  | 2017-06-30 |  | 2018-04-01
34753 | D | L-101 |  |  | 2004 |  | E-One |  | RE-013 |  |  | 2968560 |  | 2017-06-05 | 283 | Air Brakes Sys. Leaks / Aerial Ladder Adjustment | [5 empty] | Work In Progress |  |  | David |  |  |  |  | 2017-06-30 |  | 2018-04-01
35698 | C | E-002 |  |  | 2005 |  | Ferrara |  | RE-012 |  |  | 2962660 |  | 2017-06-27 | 261 | Pump Sys. Malfunctioned | [5 empty] | WAITING ON PARTS |  |  | STEVE |  |  |  |  | 2017-08-24 |  | 2018-02-22
35697 | C | E-008 |  |  | 2005 |  | Ferrara |  | OLD E-508 |  |  | 2995132 |  | 2017-09-02 | 194 | PUMP SYSTEM, MECHANICAL SEAL, IMPELLER | [5 empty] | WAITING ON PARTS |  |  | Steve |  |  |  |  | 2017-10-15 |  | 2018-04-01
34764 | C | E-077 |  |  | 2005 |  | Ferrara |  | RE-069 |  |  | 3002829 |  | 2017-09-20 | 176 | CAUGHT ON FIRE ON FIRE SCENE | [5 empty] | WAITING ON PARTS @ BODY SHOP |  |  | Steve |  |  |  |  | 2017-12-15 |  | 2018-04-01
31132 | D | L-044 |  |  | 2000 |  | E-One |  | RL-007 |  |  | 3020456 |  | 2017-11-27 | 108 | OUTRIGGER LEAK | [5 empty] | Work In Progress |  |  | DAVID |  |  |  |  | 2017-12-15 |  | 2018-04-01
35559 | D | L-019 |  |  | 2005 |  | Ferrara |  | RL-010 |  |  | 3010581 |  | 2017-12-17 | 88 | RUNNING ROUGH | [5 empty] | Work In Progress |  |  | RUSH RUCK |  |  | 2017-11-25 |  | 2017-12-15 |  | 2018-04-01
39481 | C | L-033 |  |  | 2009 |  | Ferrara |  | RL-004 |  |  | 3036389 |  | 2018-01-21 | 53 | OIL LEAK | [5 empty] | WAITING ON PARTS |  |  | RUSSELL |  |  |  |  | 2017-01-30 |  | 2018-04-01
45401 | D | L-076 |  |  | 2016 |  | Ferrara |  | RL-093 |  |  | 3038470 |  | 2018-01-26 | 48 | HYDRAULIC MALFUNCTION | [5 empty] | Work In Progress |  |  | KERRY |  |  |  |  | 2018-02-22 |  | 2018-04-01
35694 | D | E-094 |  |  | 2005 |  | Ferrara |  | RE-000 |  |  | 3046467 |  | 2018-03-04 | 11 | Engine Overheating | [5 empty] | Work In Progress |  |  | Nino |  |  |  |  | 2018-03-30
34763 | D | E-080 |  |  | 2005 |  | Ferrara |  | RE-004 |  |  | 3048581 |  | 2018-03-05 | 10 | Brakes System | [5 empty] | WAITING ON PARTS |  |  | DAVID |  |  |  |  | 2018-03-30
43282 | D | L-016 |  |  | 2013 |  | Spartan |  | RL-012 |  |  | 3049042 |  | 2018-03-06 | 9 | HYDRAULIC LEAK, SPOOL VALVE/ ABS SENSOR | [5 empty] | Work In Progress |  |  | STEVE |  |  |  |  | 2018-03-30
43026 | D | E-033 |  |  | 2013 |  | Spartan |  | RE-046 |  |  | MWO |  | 2018-03-09 | 6 | WAITING FOR PICK-UP | [5 empty] | WAITING FOR PICK-UP |  |  | RUSH TRUCK |  |  | 2018-03-09 |  | 2018-03-12
35558 | D | L-004 |  |  | 2005 |  | Ferrara |  | RL-012 |  |  | 3050507 |  | 2018-03-12 | 3 | Rear Suspension Air Bags Leaking | [5 empty] | Work In Progress |  |  | Steve & Guy |  |  |  |  | 2018-03-21